## Gantt
Section | Week
| Semester 1 | [11 empty] | Christmas |  |  |  |  | Semester 2
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Project Plan
Literature Review
Analysis and Design
Neural Network Design | [26 empty] | 1st Iteration
NN Training/Validating | [26 empty] | 2nd Iteration
NN Testing | [26 empty] | 3rd Iteration
Database
UI Development
Final Testing
Evaluation
Project Report
Documentation

## Gantt_Poster
Section | Week
| Semester 1 | [11 empty] | Christmas |  |  |  |  | Semester 2
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Project Plan (Complete)
Literature Review (Complete)
Analysis and Design (Complete)
Neural Network Design (Complete) | [26 empty] | 1st Iteration
NN Training/Validating (Complete) | [26 empty] | 2nd Iteration
NN Testing (Complete) | [26 empty] | 3rd Iteration
Database (Complete)
UI Development
Final Testing
Evaluation
Project Report
Documentation
Current Week

## Gantt (2)
Section | Week
| Semester 1 | [11 empty] | Christmas |  |  |  |  | Semester 2
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Project Plan
Literature Review
Analysis and Design
Neural Network Design | [26 empty] | 1st Iteration
NN Training/Validating | [26 empty] | 2nd Iteration
NN Testing | [26 empty] | 3rd Iteration
Database
UI Development
Final Testing
Evaluation
Project Report
Documentation